## Sheet1
Acceptance Criteria
Issue type | ID | Summary | Place
Acceptance Criteria | AEL-AC-001 | As a capstone team member, I want a GitHub repository with README and wiki, so that project work is organized and trackable. | Sprint 0 ¦ Repository and Wiki Setup
Scenario: Repository foundation setup ¦ Given a new project repository ¦ When the team initializes the repo and wiki ¦ Then the repository contains the core project metadata ¦ And team members can access the documentation location. Test Case: Open the repository and wiki links and verify the project README and team information are present. Status: Completed
Acceptance Criteria | AEL-AC-002 | As a developer, I want a runnable Python and Next.js project skeleton, so that implementation can start from a working baseline. | Sprint 0 ¦ Python and Next.js Skeleton
Scenario: Initial application skeleton ¦ Given the repository is cloned ¦ When dependencies are installed for Python and platform services ¦ Then both application layers bootstrap successfully ¦ And development can proceed on a working structure. Test Case: Run editable Python install and platform dependency install and verify no fatal bootstrap errors. Status: Completed
Acceptance Criteria | AEL-AC-003 | As an evaluator, I want YAML-based scenarios and a loader baseline, so that evaluation cases are configurable and reusable. | Sprint 0 ¦ YAML Scenario Baseline
Scenario: Scenario definition loading ¦ Given valid and invalid scenario YAML files ¦ When the loader processes them ¦ Then valid scenarios load successfully ¦ And invalid scenarios fail with clear validation errors. Test Case: Run scenario loader checks against valid and invalid YAML examples. Status: Completed
Acceptance Criteria | AEL-AC-004 | As a scrum team, I want standard templates for stories, acceptance criteria, and sprint artifacts, so that grading deliverables stay consistent. | Sprint 0 ¦ Story and Artifact Template
Scenario: Sprint documentation template setup ¦ Given the team is preparing sprint artifacts ¦ When templates are defined for stories and evidence ¦ Then required fields are standardized ¦ And future sprint documentation follows the same structure. Test Case: Review the template columns and sample sprint artifact structure for consistency. Status: Completed
Acceptance Criteria | AEL-AC-005 | As a RAG Engineer, I want a health endpoint on the target agent, so that platform connectivity checks are deterministic. | Sprint 1 ¦ RAG Service Health Endpoint
Scenario: Target agent health validation ¦ Given the target agent is running ¦ When the platform or user calls the health endpoint ¦ Then the service returns a healthy response ¦ And connectivity can be confirmed before evaluation. Test Case: Call GET /health on the built-in agent and verify HTTP 200 plus service status data. Status: Completed
Acceptance Criteria | AEL-AC-006 | As a RAG Engineer, I want a stable /agent contract, so that the evaluator can call my service consistently. | Sprint 1 ¦ Stable Query Contract
Scenario: Target agent query contract ¦ Given a valid query payload ¦ When the client calls POST /agent ¦ Then the service returns an answer payload ¦ And the response includes the expected fields for downstream evaluation. Test Case: Send a POST /agent request and validate answer Status: metadata
Acceptance Criteria | AEL-AC-007 | As an AI Application Developer, I want to register and ping my agent endpoint, so that I can validate connectivity before running evaluations. | Sprint 1 ¦ HTTP Agent Connectivity
Scenario: Agent connectivity check ¦ Given a valid agent base URL ¦ When the user runs a connection test ¦ Then the platform confirms the agent is reachable ¦ And actionable feedback is shown for success or failure. Test Case: Use /api/agent/ping with valid and invalid URLs and verify platform responses. Status: Completed
Acceptance Criteria | AEL-AC-008 | As an AI Application Developer, I want a playground to send prompts to my agent, so that I can inspect raw behavior before red-team evaluation. | Sprint 1 ¦ Pre-Evaluation Query
Scenario: Pre-evaluation sandbox query ¦ Given a connected agent and a user prompt ¦ When the user sends a query from the sandbox ¦ Then the platform shows the agent response ¦ And any available metadata or context is displayed. Test Case: Use /sandbox and POST /api/agent/query to verify response rendering. Status: Completed
Acceptance Criteria | AEL-AC-009 | As an AI Safety Engineer, I want to run a scenario bundle against an agent, so that I can detect safety and reliability violations. | Sprint 1 ¦ Run Scenario Bundle
Scenario: Scenario bundle execution ¦ Given configured provider settings and selected scenarios ¦ When an evaluation starts ¦ Then the run moves through execution states correctly ¦ And scenario-level results are stored for review. Test Case: Create a run from /dashboard/evaluations/new and verify status transitions plus persisted results. Status: Completed
Acceptance Criteria | AEL-AC-010 | As an AI Safety Engineer, I want predicate-based scoring, so that unsafe outputs are flagged with severity. | Sprint 1 ¦ Violation Classification
Scenario: Severity-based scoring ¦ Given evaluation outputs containing safe and unsafe behaviors ¦ When the scoring engine grades them ¦ Then harmful outputs receive failure labels ¦ And safe refusals or expected behaviors receive passing results. Test Case: Run scoring tests and validate PASS Status: FAIL_MINOR
Acceptance Criteria | AEL-AC-011 | As an AI Safety Engineer, I want JSON, Markdown, and HTML reports, so that I can provide reviewable evaluation evidence. | Sprint 1 ¦ Artifact Generation
Scenario: Evaluation artifact generation ¦ Given a completed evaluation ¦ When report generation runs ¦ Then JSON, Markdown, and HTML artifacts are produced ¦ And each reflects the stored evaluation results. Test Case: Download generated reports and verify they are non-empty and structurally valid. Status: Completed
Acceptance Criteria | AEL-AC-012 | As an Evaluation Operator, I want evaluation pages to auto-refresh while runs are active, so that I do not need manual navigation. | Sprint 1 ¦ Auto-Refresh Results
Scenario: Live result page refresh ¦ Given an evaluation is queued or running ¦ When the detail page is open ¦ Then the page refreshes status automatically ¦ And refresh stops after the run reaches a terminal state. Test Case: Keep an evaluation page open during execution and verify automatic updates through completion. Status: Completed
Acceptance Criteria | AEL-AC-013 | As an AI Application Developer, I want summary metrics to match detailed report data, so that score interpretation is trustworthy. | Sprint 1 ¦ Report Normalization
Scenario: Report summary normalization ¦ Given a completed evaluation with stored result data ¦ When the platform computes summary metrics ¦ Then the summary matches the detailed report contents ¦ And the displayed counts and scores remain consistent. Test Case: Compare UI summary values with the downloaded JSON report for the same evaluation. Status: Completed
Acceptance Criteria | AEL-AC-014 | As a DevOps Engineer, I want CI to execute evaluations automatically, so that unsafe regressions are caught before merge. | Sprint 2 ¦ Automated Evaluation Workflow
Scenario: CI evaluation execution ¦ Given a code change triggers the workflow ¦ When the GitHub Actions evaluation job runs ¦ Then the workflow executes the evaluation steps ¦ And generated reports are uploaded as artifacts when available. Test Case: Trigger the workflow and verify evaluation execution plus artifact upload behavior. Status: Completed
Acceptance Criteria | AEL-AC-015 | As an AI Safety Engineer, I want broader scenario coverage across jailbreak, prompt injection, PII, hallucination, and related risks, so that evaluation reflects real-world attack patterns. | Sprint 2 ¦ Expanded Adversarial Coverage
Scenario: Expanded scenario catalog loading ¦ Given the scenario directory contains the full library ¦ When scenarios are loaded and executed ¦ Then the platform recognizes the expanded scenario set ¦ And evaluations can run across multiple threat categories. Test Case: Load the scenario catalog and verify broad coverage categories are available for selection and execution. Status: Completed
Acceptance Criteria | AEL-AC-016 | As an Enterprise AI Safety and Compliance Engineer, I want release-gate decisions with policy-based GO or BLOCK results, so that I can determine whether an agent is safe for deployment. | Sprint 2 ¦ Release Gate Decision
Scenario: Release-gate policy enforcement ¦ Given a completed release-candidate evaluation ¦ When the policy gate is checked ¦ Then the system returns a GO or BLOCK decision ¦ And the decision is based on configured policy rules. Test Case: Use the release gate flow and verify policy-driven decision output for a completed evaluation. Status: Completed
Acceptance Criteria | AEL-AC-017 | As an Enterprise AI Safety and Compliance Engineer, I want downloadable evidence artifacts, so that audit packages can be reviewed externally. | Sprint 2 ¦ Evidence Artifact Download
Scenario: Evidence artifact generation ¦ Given a completed evaluation ¦ When the user requests an evidence artifact ¦ Then the platform returns the artifact successfully ¦ And the artifact corresponds to the evaluation result set. Test Case: Download the evidence artifact from the evaluation detail page or API and verify file generation. Status: Completed
Acceptance Criteria | AEL-AC-018 | As a RAG Engineer, I want grounding, contradiction, and missing-context scenarios, so that hallucinations and unsupported answers are measurable. | Sprint 2 ¦ RAG Reliability and Hallucination Scenarios
Scenario: RAG reliability scenario execution ¦ Given a RAG-targeted evaluation run ¦ When grounding and contradiction scenarios are executed ¦ Then unsupported or incorrect behaviors are surfaced ¦ And grounded responses are evaluated against expectations. Test Case: Run RAG-specific scenarios and inspect failure reasons related to missing context or contradiction. Status: Completed
Acceptance Criteria | AEL-AC-019 | As an Evaluation Operator, I want clearer monitoring for evaluation progress, so that long-running jobs are easier to manage. | Sprint 2 ¦ Evaluation Monitoring and Control
Scenario: Evaluation progress visibility ¦ Given an evaluation is active ¦ When the user opens monitoring views ¦ Then the platform shows current run status clearly ¦ And the user can distinguish active, completed, and failed states. Test Case: Use evaluation detail and list views to verify status visibility across active and terminal runs. Status: Completed
Acceptance Criteria | AEL-AC-020 | As a Platform Team Member, I want batch evaluation for multiple agent candidates, so that I can compare variants using the same scenario set. | Sprint 3 ¦ Candidate Bakeoff
Scenario: Batch candidate evaluation ¦ Given multiple configured agent candidates and a shared scenario bundle ¦ When the user starts a batch run ¦ Then the platform creates evaluations for each candidate ¦ And aggregated comparison results are produced. Test Case: Create a batch from /dashboard/batches/new and verify batch execution plus comparison output. Status: Completed
Acceptance Criteria | AEL-AC-021 | As a Platform Team Member, I want regression comparison across runs, so that I can detect quality drops before release. | Sprint 3 ¦ Baseline Regression Check
Scenario: Baseline regression analysis ¦ Given a baseline result and a candidate result ¦ When the platform compares them ¦ Then regressions are identified ¦ And the comparison is surfaced in the results workflow. Test Case: Use the regression flow and verify baseline-versus-candidate comparison results. Status: Completed
Acceptance Criteria | AEL-AC-022 | As a Compliance Engineer, I want threat-model coverage checks, so that I can verify required safety categories before approval. | Sprint 3 ¦ Threat Model Coverage Check
Scenario: Threat coverage validation ¦ Given a set of selected release scenarios ¦ When the platform checks threat coverage ¦ Then covered and missing categories are identified ¦ And release readiness is blocked when required coverage is incomplete. Test Case: Use the coverage flow and verify missing versus covered threat categories for a release setup. Status: Completed
Acceptance Criteria | AEL-AC-023 | As an Admin or Release Manager, I want versioned release-gate policies, so that I can activate and manage policy changes over time. | Sprint 3 ¦ Policy Version Management
Scenario: Policy version activation ¦ Given multiple release-gate policy versions ¦ When an administrator activates one version ¦ Then the chosen policy becomes active ¦ And subsequent gate checks use that version. Test Case: Use the policy management flow or API to create and activate a release-gate policy version. Status: Completed
Acceptance Criteria | AEL-AC-024 | As an Enterprise Admin, I want role-based controls for evaluator, release manager, and admin workflows, so that sensitive actions are restricted appropriately. | Sprint 3 ¦ RBAC Enforcement
Scenario: Role-based access enforcement ¦ Given a user with a defined application role ¦ When the user attempts a restricted action ¦ Then access is allowed or denied based on role ¦ And the platform enforces the permission boundary consistently. Test Case: Verify restricted workflows behave differently for allowed versus disallowed roles. Status: Completed
Acceptance Criteria | AEL-AC-025 | As an AI Platform Owner, I want drift monitoring across historical and current runs, so that I can detect quality changes over time. | Sprint 3 ¦ Drift Monitoring
Scenario: Drift analysis execution ¦ Given baseline historical results and current evaluation data ¦ When a drift check runs ¦ Then the platform reports quality changes over time ¦ And the results are available for review. Test Case: Use the drift monitoring flow and verify baseline-versus-current analysis output. Status: Completed
Acceptance Criteria | AEL-AC-026 | As an AI Platform Owner, I want signed audit alerts for important evaluation events, so that external systems can trust notifications. | Sprint 3 ¦ Signed Audit Alerts
Scenario: Signed audit event emission ¦ Given a configured webhook and a relevant evaluation event ¦ When the platform emits an audit event ¦ Then the payload is signed ¦ And the receiving system can validate the event source. Test Case: Trigger an audit test event and verify signed webhook behavior through the audit event flow. Status: Completed
Acceptance Criteria | AEL-AC-027 | As an AI Safety Engineer, I want targeted adversarial scenario generation by threat type, so that I can expand red-team coverage quickly. | Sprint 3 ¦ Adversarial Scenario Generation
Scenario: Adversarial scenario generation ¦ Given a selected threat category and a generation request ¦ When the user generates scenarios ¦ Then the platform returns targeted scenario content ¦ And the generated scenarios can be reviewed or persisted. Test Case: Use /api/scenarios/generate-adversarial and verify output for a chosen threat category. Status: Completed
Acceptance Criteria | AEL-AC-028 | As an External Client or CI User, I want scoped API keys, so that I can trigger evaluations without relying on browser sessions. | Sprint 3 ¦ Tenant API Keys
Scenario: API key-based access ¦ Given a valid tenant API key ¦ When the client calls a supported evaluation endpoint ¦ Then the platform authenticates the request ¦ And the operation succeeds according to the granted scope. Test Case: Use a tenant API key against supported evaluation endpoints and verify authenticated access. Status: Completed
Acceptance Criteria | AEL-AC-029 | As an External Evaluator, I want a bring-your-agent onboarding flow, so that I can connect my own HTTP agent without cloning the repository. | Sprint 3 ¦ Bring Your Agent Flow
Scenario: Self-serve external agent onboarding ¦ Given an external HTTP agent URL ¦ When the user connects, detects, tests, and runs a quick evaluation ¦ Then the platform completes onboarding through the browser ¦ And the agent can be evaluated without local code changes. Test Case: Use /bring-your-agent and verify connect Status: detect